SPECIFICATION REVIEW REPORT

Project: CWTP Ozone Tower — Pipe Expansion Joints Replacement    Owner: Greater Vancouver Water District    Jacobs Project: CE891100    Date: June 2026    Page 1 of 3

Document: 01 20 01 — Measurement and Payment

Section Reference: Section 3 Execution (§3.1.1 – §3.1.3)

| Section Ref | Issue / Finding | Severity | Recommended Action |
| --- | --- | --- | --- |
| §3.1.1 – §3.1.3 | Payment milestones sum to 105% (45% + 25% + 35%) for all three supply items — Items 1.1, 1.2 and 1.3 | CRITICAL | Must be corrected to 100% before contract award — likely reduce final milestone from 35% to 30% |

Document: Price Schedule — Division 1 — Project Management and Coordination Items

Section Reference: Items 1.5.6, 2.10, 4.10

| Schedule Item | Issue / Finding | Severity | Recommended Action |
| --- | --- | --- | --- |
| Div 1 — Item 1.5.6 | Schedule description adds 'and any other Submittals' beyond what Spec §3.1.5.6 defines — broadens scope ambiguously and exposes Contractor to undefined deliverable obligations | MODERATE | Align schedule description exactly with specification language to avoid scope disputes at payment time |
| Div 1 — Item 2.10 | Catch-all 'Other Items' line requires bidder to specify separately — risk if left blank at tender submission | MODERATE | Ensure all bidders complete this field; clarify in tender documents what is already captured in other items |
| Div 1 — Item 4.10 | Extended warranty references 'Item 1.90 above' — no Item 1.90 exists anywhere in the schedule | CRITICAL | Identify the correct base warranty item number and correct the cross-reference before contract award |

Document: Price Schedule — Division 40 — Equipment Fabrication and Delivery Items

Section Reference: Items 1.40, 2.20, 4.20

| Schedule Item | Issue / Finding | Severity | Recommended Action |
| --- | --- | --- | --- |
| Div 40 — Item 1.40 | Delivery to Site priced per 'Unit' — Spec §3.1.4 describes a single lump sum delivery event with no defined unit | MODERATE | Confirm definition of one 'unit' or change pricing basis to L.S. |
| Div 40 — Item 2.20 | Catch-all 'Other Items' line requires bidder to specify — risk of blank submission | MODERATE | Ensure all bidders complete this field at tender submission |
| Div 40 — Item 4.20 | Storage of Goods (12 weeks provisional) has no defined trigger condition in spec or schedule | MODERATE | Define activation conditions in contract (e.g. Owner-caused delay beyond agreed delivery window) |

Document: Price Schedule — Division 1 & Division 40  vs  Spec 01 20 01 — Quantities Cross-Reference Check

Section Reference: Div 40 Items 1.10–1.40, 4.20 | Div 1 Items 1.5.1–1.5.7, 2.10, 4.10 | Spec §3.1.1–§3.1.5

| Schedule Item | Description | Qty | Unit | Spec Reference and Notes | Status |
| --- | --- | --- | --- | --- | --- |
| Div 40 — Item 1.40 | Delivery to Site | 1 | Unit* | Spec §3.1.4: implies L.S. — see Table 1C | FLAG |
| Div 1 — Item 2.10 / Div 40 — Item 2.20 | Other Items (catch-all) | 1 | L.S. | Must be completed by bidder — see Tables 1B & 1C | FLAG |
| Div 1 — Item 4.10 | Provisional: Extended 2-Year Warranty | 1 | L.S. | References non-existent Item 1.90 — see Table 1B | FAIL |
| Div 40 — Item 4.20 | Provisional: Storage of Goods | 12 | Week | Trigger condition undefined — see Table 1C | FLAG |

FLAG = clarification required before award   |   FAIL = error must be corrected before award   |   Items consistent with spec not shown

SPECIFICATION REVIEW REPORT

Project: CWTP Ozone Tower — Pipe Expansion Joints Replacement    Owner: Greater Vancouver Water District    Jacobs Project: CE891100    Date: June 2026    Page 2 of 3

Document: 01 11 00 — Summary of Work

Section Reference: Section 1.2 Submittals (§1.2.6)

| Section Ref | Requirement / Finding | Severity | Recommended Action |
| --- | --- | --- | --- |
| §1.2.6 | O&M Manual must include 5 specific content elements and be delivered with goods — risk of non-compliant manual delaying final acceptance | MODERATE | Begin O&M Manual preparation early in the contract; do not leave to the delivery stage; confirm all 5 required elements are addressed |

Document: 01 11 00 — Summary of Work

Section Reference: Section 1.4 Sequencing and Section 1.5 – 1.6 Schedule (§1.4.1, §1.4.2.4, §1.5.2, §1.6.2, §1.6.3)

| Section Ref | Requirement / Risk | Severity | Recommended Action |
| --- | --- | --- | --- |
| §1.4.1 | No work may commence until Metro Vancouver approves the submitted schedule — approval delay directly delays contract start | MODERATE | Submit schedule within days of award; follow up proactively to obtain timely approval |
| §1.4.2.4 | Only one ozone train may be isolated at a time — prevents concurrent work on both trains | HIGH RISK | Build sequential train isolation into programme; assess realistic impact on contract duration and price accordingly |
| §1.5.2 | Initial site visit may be delayed up to 91 days (13 weeks) after Notice to Proceed | MODERATE | Price Item 1.5.1 monthly PM fees to cover this full potential overhead period |
| §1.6.2 | Contractor's own RFP submittal delivery timeline becomes the contractual delivery deadline | MODERATE | Ensure proposed delivery schedule in RFP is realistic and includes contingency — it will be held to |
| §1.6.3 | Late delivery: Contractor liable for ALL costs incurred by the Corporation attributable to late delivery — no financial cap stated | CRITICAL | Negotiate a liability cap or cap formula before contract execution; this is a major financial exposure at a critical water treatment facility |

Document: 01 11 00 — Summary of Work

Section Reference: Section 1.7 Delivery and Section 1.8 Drawings (§1.7.3, §1.8.6)

| Section Ref | Requirement / Risk | Severity | Recommended Action |
| --- | --- | --- | --- |
| §1.7.3 | If Metro Vancouver storage facility is unavailable, Contractor must arrange and pay for storage at own expense until Metro Vancouver is ready to receive goods | MODERATE | Ensure Div 40 Item 4.20 provisional storage (12 weeks) is priced to cover this risk; confirm storage trigger with Owner |
| §1.8.6 | Corporation may supplement or supersede Drawings for 'minor' modifications without issuing a change order — 'minor' is not defined | MODERATE | Request a clear definition or threshold for 'minor' in the contract to protect against scope creep |

Document: 01 11 00 — Summary of Work

Section Reference: Section 1.9 Unit Responsibility (§1.9.2, §1.9.3)

| Section Ref | Requirement / Risk | Severity | Recommended Action |
| --- | --- | --- | --- |
| §1.9.2 | Agents, representatives, or entities that are not a direct division of the successful Proponent cannot substitute as the Unit Responsibility Manufacturer | MODERATE | Confirm corporate relationship with manufacturer clearly in RFP submission; distributors and agents are excluded |
| §1.9.3 | Unit Responsibility Manufacturer must warrant all components including those not manufactured by them — gaskets, isolation kits, bolting hardware | MODERATE | Review all third-party components; obtain back-to-back warranties from sub-suppliers before contract execution |

Document: 01 11 00 — Summary of Work

Section Reference: Section 3.5 Quality Assurance (§3.5.1)

| Section Ref | Requirement / Risk | Severity | Recommended Action |
| --- | --- | --- | --- |
| §3.5.1 | Metro Vancouver may conduct QA inspection at the delivery point prior to off-loading, at their discretion — could delay unloading and acceptance | MODERATE | Coordinate QA inspection scheduling well in advance of delivery; build waiting time allowance into delivery logistics and confirm with Owner |

SPECIFICATION REVIEW REPORT

Project: CWTP Ozone Tower — Pipe Expansion Joints Replacement    Owner: Greater Vancouver Water District    Jacobs Project: CE891100    Date: June 2026    Page 3 of 3

Document: Cross-Reference: 01 20 01 Measurement & Payment  |  01 11 00 Summary of Work  |  Price Schedule — Inter-Document Consistency Check

Section Reference: All sections — inconsistencies and conflicts between documents

| Topic | 01 20 01 / Price Schedule Reference | 01 11 00 Reference | Finding and Required Action |
| --- | --- | --- | --- |
| Payment milestone % error | 01 20 01 — §3.1.1, §3.1.2, §3.1.3 | Not referenced in 01 11 00 | CRITICAL: milestones total 105% in all three supply items — must be corrected to 100% before award |
| Item 4.20 storage trigger undefined | Price Schedule — Div 40 Item 4.20 | 01 11 00 — §1.7.3 | §1.7.3 explains the storage scenario but no contract trigger is defined — add activation condition to contract |
| Unit Responsibility — distributor exclusion | Not addressed in 01 20 01 or Price Schedule | 01 11 00 — §1.9.2 | Exclusion of agents and distributors not reflected in tendering documents — enforce explicitly at RFP stage |
| Uncapped financial liability — two clauses | 01 20 01 — §1.3.3 (quantity risk, no re-opener) | 01 11 00 — §1.6.3 (late delivery, no cap) | Both specs expose Contractor to open-ended financial risk — negotiate caps on both before contract execution |
| Two ITPs required vs one L.S. price | Price Schedule — Div 1 Item 1.5.6 (single L.S.) | 01 11 00 — §1.1.3.5 (two separate ITPs required) | Confirm that the Item 1.5.6 lump sum price explicitly covers preparation of both ITP documents |

Severity Legend:  CRITICAL — must be resolved before contract award     HIGH RISK — significant financial or programme exposure, action required     MODERATE — manage proactively before or at contract execution

End of Review Report   |   Issued for Final Review   |   RFP XX-XXX   |   Jacobs Project CE891100   |   June 2026